## Sprint 1
Sprint 1
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Draw ERD | Draw ERD diagram | DucNDM,NhatNQ | Done | 8 | 6 | 5 | 5 | 5 | 5 | 5 | 5 | 4
Draw usecase diagram | Draw usecase diagram | ThongVM,DucNDM | Done | 8 | 7 | 5 | 5 | 5 | 5 | 5 | 5 | 4
Design mockup UI | - Loading screen | TrinhHC | Done | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
| - Register screen | TrinhHC | Done | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
| - Login screen | TrinhHC | Done | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
| - Forget password screen | TrinhHC | Done | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
| - Home screen | TrinhHC | Done | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
| - Setting screen | TrinhHC | Done | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
| - Account profile screen | TrinhHC | Done | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
| - Account setting screen | TrinhHC | Done | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
| - All roomates screen | TrinhHC | Done | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
| - All rooms screen | TrinhHC | Done | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
| - Filter Bookmark Room screen | TrinhHC | Done | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
| - Bookmark screen | TrinhHC | Done | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
| - Notification screen | TrinhHC | Done | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
| - Search screen | TrinhHC | Done | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
| - Room detail screen | TrinhHC | Done | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
| - Roomate detail screen | TrinhHC | Done | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
| - Create room screen | TrinhHC | Done | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
| - Create roomate screen | TrinhHC | Done | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
Report 1 | Introduction, current situation | NhatNQ,ThongVM | Done | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5
| Problem definition | NhatNQ | Done | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0
| Proposed solution | NhatNQ,ThongVM | Done | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0
| Functional requirement, role responsibility | ThongVM | Done | 0.5 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0
| Total |  |  | 57.5 | 45 | 32 | 32 | 30.75 | 30.5 | 30.5 | 30.5 | 17.5

## Sprint 2
Sprint 2
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Fix ERD | Draw ERD diagram | DucNDM,NhatNQ | Done | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Fix usecase diagram | Draw usecase diagram | DucNDM,NhatNQ | Done | 8 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement UI | - Loading screen | ThongVM | Done | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| - Register screen | ThongVM | Done | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| - Login screen | ThongVM | Done | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| - Forget password screen | ThongVM | Done | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| - Setting screen | ThongVM | Done | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| - Account profile screen | ThongVM | Done | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| - Bookmark screen | TrinhHC | Done | 4 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| - Notification screen | TrinhHC | Done | 4 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| Total |  |  | 36 | 23 | 8 | 8 | 8 | 8 | 8 | 0 | 0

## Sprint 3
Sprint 3
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Draw sequence diagram | - Draw sequence diagram | DucNDM,ThongVM | Not Done | 16 | 16 | 16 | 16 | 10 | 2 | 2 | 2 | 2
Implement UI | - Room detail for owner screen | TrinhHC | Done | 16 | 12 | 4 | 1.5 | 1.5 | 1 | 1 | 1 | 0
| - Room detail for member screen | TrinhHC | Done | 8 | 8 | 8 | 8 | 3 | 2 | 1 | 1 | 0
| - Filter Bookmark Room screen | TrinhHC | Done | 8 | 8 | 8 | 3 | 1 | 1 | 1 | 1 | 0
Implement APIs | - Create user | DucNDM | Done | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| - Get user by username | DucNDM | Done | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| - Get user by id | DucNDM | Done | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| - Update user by id | DucNDM | Done | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
Implement Euclidean | - Demo Recommendation Systen | NhatNQ | Done | 24 | 24 | 24 | 18 | 10 | 4 | 3 | 1 | 0
Report 2 | - Problem Definition | ThongVM | Done | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| - Project organization | ThongVM | Done | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| - Project management plan | ThongVM | Done | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  |  | 80 | 76 | 68 | 46.5 | 25.5 | 10 | 6 | 4 | 0

## Sprint 4
Sprint 4
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Draw sequence diagram | Login | ThongVM | Done | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0
| Create Room | ThongVM | Done | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Update Room | ThongVM | Done | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Delete Room | ThongVM | Done | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| View Single Room | ThongVM | Done | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| View Suggested Room | ThongVM | Pending | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5 | 1.5
| Add Member into Room | ThongVM | Done | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Search Post | ThongVM | Pending | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Create Post | DucNDM | Done | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Update Post | DucNDM | Done | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Delete Post | DucNDM | Done | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Create Partner Post | DucNDM | Done | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Update Partner Post | DucNDM | Done | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Delete Partner Post | DucNDM | Done | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| View Single Post | DucNDM | Done | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
| Remove Member of Room | DucNDM | Done | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
Implement UI | - All Suggest Room screen | TrinhHC | Done | 8 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - All Suggest Roommatte scren | TrinhHC | Done | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - All roomates screen | TrinhHC | Done | 8 | 8 | 8 | 5 | 5 | 0 | 0 | 0 | 0
| - All rooms screen | TrinhHC | Done | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0
| - Filter Bookmark Roommate screen | TrinhHC | Done | 8 | 8 | 8 | 8 | 8 | 8 | 4 | 0 | 0
| - Createroom screen for owner | ThongVM | Done | 8 | 8 | 4 | 4 | 4 | 0 | 0 | 0 | 0
| - Filter All Roommate screen | ThongVM | Done | 8 | 8 | 8 | 8 | 8 | 5 | 0 | 0 | 0
| - Filter Room Search Result | ThongVM | Done | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0
| - Filter Roommate Search Result | ThongVM | Done | 8 | 8 | 8 | 8 | 8 | 3 | 0 | 0 | 0
Implement APIs | - Create Image | DucNDM | Pending | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
| - Remove Image | DucNDM | Done | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| - Create Post | NhatNQ | Done | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Update Post | NhatNQ | Done | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Remove Post | NhatNQ | Done | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Create Favourite | NhatNQ | Done | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - View all Post | NhatNQ | Not Done | 16 | 16 | 16 | 11 | 7 | 3 | 3 | 3 | 3
| - Remove Favourite | NhatNQ | Done | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| - View all Favourites | NhatNQ | Done | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| - Remove Room | NhatNQ | Done | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| - Suggest nearby room masters | DucNDM | Done | 20 | 20 | 20 | 18 | 18 | 13 | 0 | 0 | 0
| Total |  |  | 142 | 137 | 116 | 99.5 | 85.5 | 56.5 | 15.5 | 11.5 | 11.5

## Sprint 5
Sprint 5
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Draw sequence diagram | View Suggested Partner List | ThongVM | Done | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Register | ThongVM | Done | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Search Post | ThongVM | Done | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement UI | - Suggest Setting | TrinhHC | Done | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Room detail screen for Master | TrinhHC | Done | 8 | 8 | 8 | 6 | 0 | 0 | 0 | 0 | 0
| - Create roomate post screen | TrinhHC | Done | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Create Room post screen | TrinhHC | Done | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0
| - Edit room screen for owner | TrinhHC | Done | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0
| - Room owner Signup Screen | ThongVM | Done | 8 | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0
| - Guest Suggest Signup Screen | ThongVM | Done | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0
| - Notification screen Detail | ThongVM | Done | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0
Implement APIs | - Adding pageable for all APIs | DucNDM | Done | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Search post (using Criteria) | NhatNQ | Done | 30 | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0
| - Send email | DucNDM | Done | 18 | 18 | 12 | 12 | 10 | 6 | 1 | 0 | 0
| - View all Rooms | NhatNQ | Done | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Add room member | DucNDM | Done | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Data Extraction | - Insert data for city and district | ThongVM | Done | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total |  |  | 140 | 92 | 68 | 50 | 34 | 14 | 1 | 0 | 0

## Sprint 6
Sprint 6
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Fix Bugs | - Filter does not return correct results | NhatNQ | Done | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Cannot create room | DucNDM | Done | 12 | 12 | 4 | 0 | 0 | 0 | 0 | 0 | 0
| - Create room post permission | DucNDM | Done | 8 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Implement APIs | - Suggest posts for member | NhatNQ | Done | 32 | 32 | 22 | 14 | 10 | 0 | 0 | 0 | 0
| - Create roommate post | DucNDM | Done | 8 | 8 | 8 | 4 | 0 | 0 | 0 | 0 | 0
| - Get city | DucNDM | Done | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Get district | DucNDM | Done | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0
| - Remove post | NhatNQ | Done | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement UI and mapping API | - Filter screen | ThongVM | Done | 10 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - All Tab Screen | ThongVM | Done | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0
| - Room master detail screen | TrinhHC | Done | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0
| - Member detail screen | TrinhHC | Done | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0
| - Home Screen for Member | TrinhHC | Done | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Bookmark Tab screen | TrinhHC | Done | 10 | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Document | - Report 3 | ThongVM | Done | 13 | 13 | 13 | 6 | 0 | 0 | 0 | 0 | 0
| Total |  |  | 140 | 114 | 75 | 48 | 30 | 10 | 0 | 0 | 0

## Sprint 7
Sprint 7
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Fix Bugs | - Filter not loaded by city | NhatNQ | Done | 12 | 8 | 2 | 2 | 2 | 2 | 2 | 2 | 0
Implement APIs | - Suggest nearby room master | DucNDM | Done | 30 | 22 | 20 | 10 | 4 | 4 | 4 | 4 | 4
| - Suggest newest post for member | NhatNDM | Done | 30 | 30 | 30 | 20 | 14 | 3 | 3 | 3 | 3
| - Remove member from room | DucNDM | In Progress | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
| - Show member detail | DucNDM | Done | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
Implement UI | - Account Tab Screen for Roomowner | TrinhHC | Done | 10 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| - Account Tab Screen for Member | TrinhHC | In Progress | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| - Home Screen for owner | TrinhHC | Done | 10 | 10 | 10 | 10 | 5 | 5 | 3 | 0 | 0
Google API | - Auto complete for address searching | TrinhHC | Done | 10 | 10 | 10 | 10 | 4 | 2 | 2 | 2 | 0
Document | - Class Diagram | ThongVM | Done | 10 | 10 | 10 | 10 | 2 | 0 | 0 | 0 | 0
| - Architecture Diagram | ThongVM | Done | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0
| - Component Diagram | ThongVM | Done | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0
| - Conceptual Diagram | ThongVM | Done | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Report 4 | ThongVM | In Progress | 10 | 6 | 2 | 2 | 2 | 2 | 2 | 2 | -5
|  |  |  | 160 | 135 | 123 | 88 | 53 | 38 | 32 | 29 | 18

## Sprint 8
Sprint 8
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Fix Bugs | - Suggest roomaster not paging | DucNDM | Done | 12 | 12 | 12 | 12 | 12 | 4 | 0 | 0 | 0
| - Delete room not follow bussiness logic | NhatNQ | Done | 18 | 18 | 15 | 10 | 5 | 0 | 0 | 0 | 0
Implement APIs | - Edit room member | DucNDM | In Progress | 24 | 20 | 20 | 16 | 10 | 2 | 2 | 2 | -10
| - Upload image (using Amazon S3) | TrinhHC | Done | 15 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0
| - Room detail for house owner | ThongVM | Done | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Update Room | ThongVM | Done | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Check permission for post type | NhatNQ | Done | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0
Implement UI and Map API | - Account Tab Screen for Member | TrinhHC | Done | 10 | 10 | 10 | 5 | 5 | 5 | 5 | 5 | 5
| - Edit room member screen | TrinhHC | Done | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0
Document | - Fix diagrams | NhatNQ | Done | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Report 4 | ThongVM | Done | 5 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 0
| - Report 5 | ThongVM | In Progress | 15 | 15 | 15 | 15 | 10 | 10 | 5 | 0 | -10
|  |  |  | 144 | 117 | 96 | 77 | 46 | 25 | 16 | 7 | -15

## Sprint 9
Sprint 9
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Fix Bugs | - Edit room member | TrinhHC | Done | 10 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
Implement APIs | - View member posts | NhatNQ | Done | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - View room master posts | NhatNQ | Done | 4 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| - View current room | DucNDM | Done | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0
| - View room history | NhatNQ | Done | 8 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Approve room | NhatNQ | Done | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 2 | 2
| - Suggest nearby for member | DucNDM | Done | 27 | 20 | 20 | 15 | 10 | 6 | 0 | 0 | 0
Implement Mobile UI and Map API | - Notification screen | TrinhHC | Done | 12 | 8 | 6 | 0 | 0 | 0 | 0 | 0 | 0
| - Edit room screen | TrinhHC | Done | 12 | 12 | 12 | 12 | 4 | 4 | 4 | 4 | 4
Implement WebUI | - Manage user page | NhatNQ | Done | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0
| - Manage room page | ThongVM | Done | 10 | 10 | 10 | 10 | 10 | 8 | 0 | 0 | 0
Document | - Report 5 | ThongVM | Done | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0
| - Fix report 1,2,3 | ThongVM | Done | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 0 | 0
|  |  |  | 138 | 109 | 102 | 85 | 54 | 38 | 9 | 9 | 9

## Sprint 10
Sprint 10
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Fix Bugs | - Fix create room post | NhatNQ | Pending | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| - Fix create roommate post | DucNDM | Pending | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| - Fix edit room post | NhatNQ | Done | 10 | 10 | 8 | 2 | 2 | 2 | 2 | 2 | 2
| - Fix edit roommate post | DucNDM | Done | 10 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| - Fix filter service | NhatNQ | Pending | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22 | 22
Implement APIs | - Create reference | ThongVM | Done | 12 | 6 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| - Firebase notification | DucNDM | Pending | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16 | 16
| - Edit reference | ThongVM | Done | 12 | 12 | 12 | 8 | 0 | 0 | 0 | 0 | 0
Implement Mobile UI and Map API | - Create room post screen | TrinhHC | Pending | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| - Search Room Post | TrinhHC | Done | 10 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Edit room post screen | TrinhHC | Pending | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
| - Edit roommate post screen | TrinhHC | Pending | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
Document | - Report 6 | ThongVM | Done | 15 | 15 | 15 | 15 | 10 | 2 | 2 | 2 | 2
|  |  |  | 157 | 107 | 99 | 95 | 82 | 74 | 74 | 74 | 74

## Sprint 11
Sprint 11
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Fix Bugs | - Fix create room post | NhatNQ | Done | 10 | 10 | 10 | 10 | 10 | 10 | 8 | 2 | 0
| - Fix create roommate post | DucNDM | Done | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0
| - Fix filter service | NhatNQ | Done | 22 | 16 | 16 | 10 | 2 | 2 | 2 | 2 | 2
| - Fix room detail | NhatNQ | Done | 12 | 12 | 12 | 12 | 12 | 3 | 0 | 0 | 0
| - Fix user detail | DucNDM | Done | 12 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Fix store procedure | DucNDM | Done | 12 | 12 | 12 | 8 | 2 | 0 | 0 | 0 | 0
Implement APIs | - Rate room | ThongVM | Done | 12 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 2
| - Rate member | ThongVM | Done | 12 | 12 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| - Search post (nearby search) | DucNDM | Done | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Implement Mobile UI and Map API | - Create room post screen | TrinhHC | Done | 12 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0
| - Edit room post screen | TrinhHC | Done | 13 | 13 | 13 | 13 | 13 | 3 | 0 | 0 | 0
| - Edit roommate post screen | TrinhHC | Done | 13 | 13 | 13 | 5 | 3 | 3 | 3 | 3 | 3
Document | - Update sequence diagram | ThongVM | Done | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
| - Update usecase details | ThongVM | Done | 10 | 10 | 10 | 2 | 2 | 2 | 2 | 2 | 2
|  |  |  | 162 | 132 | 118 | 82 | 62 | 33 | 23 | 17 | 15

## Sprint 12
Sprint 12
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Fix Bugs | - Return room rate in view post apis | DucNDM | Done | 24 | 11 | 3 | 3 | 3 | 3 | 3 | 3 | 3
| - Update create room post | DucNDM | Done | 8 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0
| - Update create roommate post | NhatNQ | Done | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Current room | DucNDM | Done | 8 | 8 | 8 | 8 | 2 | 2 | 2 | 2 | 2
| - History room | NhatNQ | Done | 8 | 8 | 8 | 8 | 8 | 8 | 2 | 2 | 2
| - Room rate | ThongVM | Done | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - User rate | ThongVM | Done | 8 | 8 | 8 | 8 | 8 | 0 | 0 | 0 | 0
Implement APIs | - Firebase notification | NhatNQ | Done | 24 | 24 | 10 | 2 | 2 | 2 | 2 | 2 | 2
Implement Mobile UI and Map API | - Update all screen with rate | TrinhHC | Done | 24 | 16 | 6 | 1 | 1 | 1 | 1 | 1 | 1
| - Get notification message | TrinhHC | Done | 13 | 13 | 13 | 13 | 10 | 4 | 1 | 1 | 1
Document | - Fix report 4,5 | ThongVM | Done | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0
| - Report 6 | ThongVM | Done | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0
|  |  |  | 143 | 106 | 74 | 53 | 34 | 20 | 11 | 11 | 11

## Sprint 13
Sprint 13
Backlog Item | Sprint task | Responsible | Status | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Sprint Review
Fix Bugs | - Suggest api | NhatNQ | Done | 30 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0
| - Delete finding room post api | DucNDM | Done | 15 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Refactor functions for all apis | DucNDM | Done | 15 | 15 | 10 | 5 | 0 | 0 | 0 | 0 | 0
| - Add member | ThongVM | Done | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Search | NhatNQ | Done | 15 | 15 | 15 | 10 | 5 | 0 | 0 | 0 | 0
Fix Mobile UI and Map API | - User details | TrinhHC | Done | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| - Post details | TrinhHC | Done | 15 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0
| - Notification details | TrinhHC | Done | 15 | 15 | 15 | 5 | 0 | 0 | 0 | 0 | 0
Document | - Fix report 6 | ThongVM | Done | 15 | 15 | 5 | 0 | 0 | 0 | 0 | 0 | 0
| - Report summary | ThongVM | Done | 15 | 15 | 15 | 5 | 0 | 0 | 0 | 0 | 0
|  |  |  | 145 | 115 | 60 | 20 | 5 | 0 | 0 | 0 | 0